**Milestone List**

|  |  |  |  |
| --- | --- | --- | --- |
| **Milestone ID** | **Milestone Name** | **Description** | **Planned Date** |
| M1 | Project Initiation | Official project approval | Day 1 |
| M2 | Funding Secured | Completion of funding round | Day 45 |
| M3 | Online Platform Ready | Testing and deployment of platform | Day 90 |
| M4 | Legal Approvals Granted | All regulatory permits acquired | Day 120 |
| M5 | Staff Trained | Completion of training for staff | Day 150 |
| M6 | Marketing Campaign Launched | Digital and offline campaigns live | Day 180 |
| M7 | Full Service Launch | Delivery operations begin | Day 200 |