**ASSUMPTION LOG**

**PROJECT NAME:** GreenLeaf Medical Delivery  
**PROJECT MANAGER:** Arun Goud & Rutul Patel  
**CLIENT:** GreenLeaf Medical Delivery  
**DATE:** MM/DD/YYYY

**Assumptions Table**

| **ASSUMPTION NO.** | **DATE IDENTIFIED** | **ASSUMPTION DESCRIPTION** | **VALIDATION ASSIGNED TO** | **VALIDATION DUE DATE** | **DATE OF LAST UPDATE** | **COMMENTS** |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | MM/DD/YYYY | All necessary **state licenses** and **permits** will be obtained without significant delays. | Project Managers | MM/DD/YYYY | MM/DD/YYYY | Delays in licensing may impact project timeline. |
| 2 | MM/DD/YYYY | **Funding** will be secured from private investors and grant opportunities to support the estimated budget of **$140,000 - $240,000**. | Finance Team | MM/DD/YYYY | MM/DD/YYYY | Budget constraints may require scope adjustments. |
| 3 | MM/DD/YYYY | Sufficient **market demand** exists for a legally compliant **medical marijuana delivery service** in Bridgeport, CT. | Market Research Team | MM/DD/YYYY | MM/DD/YYYY | Demand will be reassessed during launch phase. |
| 4 | MM/DD/YYYY | **Partnerships** with licensed **dispensaries** will be established without major legal or logistical challenges. | Business Development Team | MM/DD/YYYY | MM/DD/YYYY | Any issues in partnerships could delay product availability. |
| 5 | MM/DD/YYYY | The **website and mobile app** will be successfully developed and tested within **four months**. | IT Team | MM/DD/YYYY | MM/DD/YYYY | Delays in testing may affect launch schedule. |
| 6 | MM/DD/YYYY | Compliance with **HIPAA and state regulatory requirements** will be maintained throughout the project. | Compliance Team | MM/DD/YYYY | MM/DD/YYYY | Non-compliance could result in legal actions or fines. |
| 7 | MM/DD/YYYY | Adequate **staff will be hired and trained** within the planned timeline. | HR Team | MM/DD/YYYY | MM/DD/YYYY | Staffing shortages could impact service quality. |
| 8 | MM/DD/YYYY | The **delivery system** will operate securely, ensuring safe and **timely transportation** of medical cannabis. | Operations Team | MM/DD/YYYY | MM/DD/YYYY | Security failures may result in compliance violations. |