## Sheet1
WBS Code | Activity | Start Date | End Date
1.0 | Project Planning & Initiation | 2025-03-01 | 2025-04-17
1.1 | Develop business plan | 2025-03-12 | 2025-03-27
1.2 | Secure funding and investment | 2025-03-28 | 2025-04-17
1.3 | Obtain legal and regulatory approvals | 2025-04-18 | 2025-05-18
1.4 | Define project scope and objectives | 2025-03-01 | 2025-03-11
1.5 | Identify key stakeholders | 2025-03-01 | 2025-03-11
2.0 | Technology & Infrastructure Development | 2025-04-18 | 2025-06-17
2.1 | Design and develop a secure online ordering platform | 2025-04-18 | 2025-06-02
2.1.1 | Define software requirements | 2025-04-18 | 2025-04-25
2.1.2 | Develop web and mobile applications | 2025-04-26 | 2025-05-30
2.1.3 | Integrate secure payment gateways | 2025-05-10 | 2025-05-30
2.1.4 | Implement GPS tracking for deliveries | 2025-05-31 | 2025-06-02
2.2 | Establish IT security and compliance measures | 2025-06-03 | 2025-06-17
2.2.1 | Ensure HIPAA and local legal compliance | 2025-06-03 | 2025-06-10
2.2.2 | Implement data encryption and security features | 2025-06-11 | 2025-06-17
3.0 | Operations & Logistics | 2025-06-18 | 2025-08-19
3.1 | Procure and set up delivery fleet | 2025-06-18 | 2025-07-10
3.1.1 | Acquire vehicles with secure storage | 2025-06-18 | 2025-06-24
3.1.2 | Install GPS tracking systems | 2025-06-25 | 2025-06-30
3.1.3 | Implement fleet maintenance plan | 2025-07-01 | 2025-07-10
3.2 | Develop Standard Operating Procedures (SOPs) | 2025-07-11 | 2025-07-25
3.3 | Recruit and train delivery personnel | 2025-07-26 | 2025-08-19
3.3.1 | Conduct background checks | 2025-07-26 | 2025-08-02
3.3.2 | Train drivers in compliance and safety protocols | 2025-08-03 | 2025-08-19
3.4 | Establish delivery hubs and logistics network | 2025-08-03 | 2025-08-19
3.5 | Develop inventory and supply chain management system | 2025-08-03 | 2025-08-19
4.0 | Legal & Compliance | 2025-04-18 | 2025-05-18
4.1 | Obtain required licenses and permits | 2025-04-18 | 2025-05-18
4.2 | Ensure compliance with medical marijuana regulations | 2025-04-18 | 2025-05-18
4.3 | Establish risk management and liability policies | 2025-04-18 | 2025-05-18
5.0 | Marketing & Customer Engagement | 2025-07-26 | 2025-09-15
5.1 | Develop branding and promotional materials | 2025-07-26 | 2025-08-10
5.2 | Launch digital marketing campaigns | 2025-08-11 | 2025-09-15
5.3 | Establish partnerships with medical dispensaries and healthcare providers | 2025-08-11 | 2025-09-15
5.4 | Implement customer support and feedback systems | 2025-08-11 | 2025-09-15
6.0 | Monitoring, Evaluation, & Scaling | 2025-09-16 | 2025-10-30
6.1 | Track key performance indicators (KPIs) | 2025-09-16 | 2025-09-30
6.2 | Monitor customer satisfaction and service efficiency | 2025-10-01 | 2025-10-15
6.3 | Conduct periodic compliance audits | 2025-10-01 | 2025-10-30
6.4 | Develop future expansion and scalability plan | 2025-10-16 | 2025-10-30