## Sheet1
ID | Risk Category | Risk Description | Probability | Impact | Mitigation Strategy | Owner
1 | Regulatory | Licensing and permit delays due to regulatory approvals | High | High | Early application and proactive engagement with regulators | Legal Team
2 | Technology | System security vulnerabilities and technical failures | Medium | High | Regular security audits and phased implementation of technology | IT Manager
3 | Operations | Shortage of trained delivery personnel | High | Medium | Initiate hiring campaigns early and offer retention incentives | HR Manager
4 | Funding | Delays in securing investment for project execution | Medium | High | Engage multiple investors and maintain backup funding options | Finance Team
5 | Logistics | Disruptions in supply chain affecting deliveries | Medium | Medium | Develop contingency plans with multiple suppliers | Operations Manager